Release 3.1 Turn Up Testing

Daily Status Report: 	1/18/02

# Turn Up Testing Status

## The test bed was available 100% of the time

2.   Release 3.1.0.2 was installed January 2, 2002 at 10:15 PM CST. The defect fixed is listed in the issues section of this report.

## Please see table below for test completion and issue summarization.

# Testing Completion

Notes:

- We are still waiting for some of the SPs to provide the total number of test cases they plan to execute.  Once we have that information we will add it in the  “Total Test Cases” column.

- “Total Test Case” numbers will vary from below by SP, depending on # of additional test cases executed, # of Optional test cases executed,  # of Conditional, etc.

- The “% Complete” column below is based on the total test cases Passed vs. the total number of test cases to be tested by SP represented below in the “Total Test Cases” column.

| Company | SOA/ LSMS | EDR vs NON-EDR | Test Cases Conducted | Pass/Fail /Not Supported | Total Test Cases | % Complete | Issues |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NE REGION TESTING |
| SP1 | Both | EDR | 122 | P = 122 F = 0 NS = 3 | 123 | 99% | No issues to report. 3.1.0.2 regression testing complete |
| SP2 | Both | EDR (No Dash X SOA/ LSMS) | 122 | P = 122 F = 0 NS = 24 | 122 | 100% | Testing complete for Turn Up. 3.1.0.2 regression testing complete SP received 3.1 certification |
| SP3 | Both | Non-EDR | 153 | P = 133 F = 2 NS = 18 | 153 | 100% | 3.1.0.2 regression testing complete Vendor must provide fix to correct failed test case ASAP. SP receives 3.1 certification |
| SP4 | LSMS | EDR | 67 | P =67 F = 0 NS = 12 | 67 | 100% | Testing complete for Turn Up. 3.1.0.2 regression testing complete SP received 3.1 certification |
| SP5 | 2 SOA 2 LSMS | Both | 139 | P = 139 F = 0 NS = 8 | 139 | 100% | Testing complete for Turn Up. 3.1.0.2 regression testing complete SP received 3.1 certification |
| SP6 | LSMS | EDR | 84 | P = 84 F = 0 NS = 9 | 84 | 100% | Testing complete for Turn-Up. 3.1.0.2 regression testing complete SP received 3.1 certification |
| SP7 | Both | EDR | 120 | P = 116 F =4 NS = 17 | 121 | 96% | Re-test failed test cases. 3.1.0.2 regression testing complete |
| SP8 | 1 SOA 2 LSMS | EDR | 211 | P = 222 F = 0 NS = 14 | 229 | 100% | Audit test case failure determined to be NPAC defect. SP received 3.1 certification |
| SP9 | LSMS only | Non- EDR | 60 | P = 60 | 60 | 100% | Testing complete for Turn Up. 3.1.0.2 regression testing complete SP received 3.1 certification |
| SP10 | LSMS only | Non- EDR | 57 | P = 55 F = 2 | 58 | 100% | Vendor must provide fix to correct failed test cases ASAP. 3.1.0.2 regression testing complete. SP receives Conditional 3.1 certification |
| SP11 | Both | EDR | 166 | P = 165 F = 1 NS = 30 | 166 | 99% | SP will work with vendor to correct failed case. 3.1.0.2 regression testing complete |
| SP12 | SOA only |  | 157 | P=157 | 223 | 70% | SP will support 3.1 functionality. |
| SP13 | SOA only |  | 93 | P=93 | 100 | 93% | SP will continue with LTI as SOA. |
| SP14 | SOA only | Non-EDR | 80 | P = 80 F = 0 | 156 | 51% | No issues to report. |
| SP15 | SOA only |  |  | P = 40 | 127 | 31% | Five test cases pending. |
| SP16 | SOA only |  |  | P = 66 | 135 | 49% | No issues to report. |
| SP 17 (testing for 11 SPs) | LSMS only | Both |  | P = 57 NS = 18 | 57 | 100% | Testing complete for Turn Up. regression testing complete SP received 3.1 certification |
| SP18 | LSMS only | Non-EDR |  | P = 50 | 50 | 0% | SP received 3.1 certification |
| Group Testing (Northeast) | 11 SOA 9 EDR LSMS 4 Non-EDR LSMS |  |  | P = 22 | 29 | 76% | Testing cancelled in the morning due to large number of notifications from a test case run prior to group testing and in the afternoon due to a system tunable set incorrectly so all pending SVs moved tp cancelled. |
| SUPER REGION TESTING |
| SP1 | SOA only |  |  | P = 37 | 124 | 30% | Continued testing rescheduled for 2/11. |
| SP2 |  |  |  |  |  |  |  |
| SP3 |  |  |  |  |  |  |  |
| SP4 |  |  |  |  |  |  |  |
| SP5 |  |  |  |  |  |  |  |
| SP6 |  |  |  |  |  |  |  |
| SP7 |  |  |  |  |  |  |  |
| SP8 |  |  |  |  |  |  |  |
| SP9 |  |  |  |  |  |  |  |
| SP10 |  |  |  |  |  |  |  |
| SP11 |  |  |  |  |  |  |  |
| SP12 |  |  |  |  |  |  |  |
| SP13 |  |  |  |  |  |  |  |
| SP14 |  |  |  |  |  |  |  |
| SP15 |  |  |  |  |  |  |  |
| SP16 |  |  |  |  |  |  |  |
| SP17 |  |  |  |  |  |  |  |

# Issues/Risks:

## Below is a list of all defects recorded for Rel 3.1 NE Region TUT.   This list will be published daily on this report  as well as posted to the  NPAC Secure web site.

| Incident | Date Opened | Summary | Severity | Planned Release | Status | Description | Root Cause/ Resolution | Date Closed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 91681 | 07/11/01 | Performance Testing – Delays in old SP Create requests. | 3 | 3.1 | Open | 3.0.7.0 Performance Testing – During retesting of 88128, processing slowed down and to SPs reported communication time-outs due to NPAC not responding to create requests submitted from the old SP. A ticket was opened with ESI on this incident. | This performance issue, discovered during 3.0.7.0 testing, has been resolved with the current 3.1 release now in Turn Up Testing. Once performance and volume testing by the Industry is completed on 3.1, we will close this incident. |  |
| 98542 | 11/26/01 | NPAC router memory leak | 3 |  | Open | During NeuStar’s acceptance testing for 3.1.0, a performance issue was discovered. In the code for the NPAC router there is a memory leak that causes the size of the NPAC router to grow. The router will run out of memory and needs to be rebooted to correct the problem. Any SPs on that router need to re-associated. | A ticket has been opened at DSET. DSET is working on identifying a fix. Once the fix is identified, a patch release will be issued. Severity reduced as risk re-evaluated. Leak is present in 3.0 production. |  |
| 99355 | 12/06/01 | Mass Update causes association to abort | 2 |  | Open | Inclusion of SPID in mass update filter causes the SP software to abort association. | Vendor software cannot handle SPID in the mass update filter. It is a vendor issue. |  |
| 100306 | 12/26/01 | Too many notifications on deferred disconnect | 3 | TBD | Pending | One SP reports problem, other SPs pass the test case. | Determined to be a defect. The fix will be in a release to be determined(TBD). |  |
| 100839 | 1/08/02 | NANC 179 2.33 Port to original - break in SVID, receive list of 20, expect range of 10. | 2 | 3.1.0.3 | Pending |  | Determined to be a defect. It will be fixed in 3.1.0.3. |  |
| 100898 | 1/08/02 | Remove LNP_TYPE from the filter on mass updated downloads | 3 | 3.1.0.3 | Pending | LNP_TYPE attribute causing problems in Mass Update test cases. | Feature change coded and tested in 3.1.0.3. Operational M&P: can be sent without LNP_TYPE attribute. |  |
| 101047 | 1/11/02 | Audit test case completes with errors. | 3 |  | Open | NPAC attempts to modify numberPoolBlockActivationTimeStamp. Violates gdmo. | Fix to be determined, request that attribute be modifiable. |  |
| 101139 | 1/14/02 | NPAC routers restarted in test bed in AM. | 3 |  | Open | Router restarted in testbed in AM. RCA requested. | Neustar Application Support investigating. |  |
| CLOSED TROUBLE TICKETS |
| 98968 | 11/30/01 | Test bed crashed | 1 |  | Closed | 3.1 Test Bed was unavailable from 4:44 pm Eastern to 6:00pm Eastern | The use of an application tool to assist a service provider drop a key list resulted in a database crash. The key list contained keys referenced by a process in the database. The tool has been corrected. | 11/30/01 |
| 98906 | 11/29/01 | TN stuck in progress | 2 |  | Closed | TN was stuck in progress leaving system waiting for response. Bouncing the router resolved this. | The TN was stuck in progress on the SPs side because the SP and NPAC had lost communication. Bouncing the router and re-establishing association created a new communication channel and the TNs advanced to the state they were supposed | 12/06/01 |
| 99458 | 12/07/01 | Test bed down | 1 |  | Closed | Test bed was unavailable from 4:26pm to 4:46pm and 5:34pm to 5:57pm Eastern. | The use of an ad hoc tool to assist a SP in dropping and recreating key list resulted in a database crash. | 12/07/01 |
| 98905 | 11/29/01 | Double association | 2 |  | Closed | NPAC seeing two associations from one SP. Aborting associations did not permanently fix the issue. | NPAC has no requirements to prevent this from happening. Recommend closing this issue. | 12/13/01 |
| 99352 | 12/06/01 | GUI Error | 2 |  | Closed |  | The WebGUI screen by design shows a “worst case” number as calculating the actual number would cause delay. Recommend closing this issue. | 12/13/01 |
| 100080 | 12/14/01 | Test bed was unavailable | 2 |  | Closed | 3.1 Test bed outage | PLog table had processes that remained connected. DB had to be restarted and data integrity checked before becoming available again. |
| 99349 | 12/06/01 | Mass Update not successful | 2 |  | Closed | Mass Update not successful during execution of test case NANC 68-3 | Issues with SP database. Test case passed 12/28/01 | 12/31/01 |
| 100641 | 1/03/02 | SOA Notification after Audit causes abort | 2 | 3.1.0.2 | Closed | Range Notification has null values causing association to abort. | ESI ticket 8788. missed as NPAC ticket until 1/03. Fixed in Release 3.1.0.2 | 01/03/02 |
| 100695 | 1/04/02 | Activate TNs, drop association, reassociate - core dump. | 2 |  | Closed |  | Test case 2.37 passed. | 1/07/02 |
| 100839 | 1/07/02 | Test bed unavailable. | 2 |  | Closed | 3.1 Test Bed unavailable, some shared libraries incorrectly installed | 3.1.0.2 shared libraries installed correctly. | 1/07/02 |
| 99265 | 12/05/01 | Associated SPID not receiving notifications | 2 |  | Closed | During test case NANC 48-5, the associated SPID did not receive notifications. | NPAC SD has looked at this issue and has found logs of notifications sent to the SPID. NeuStar will work with SP to resun the test case and trace what is happening. Problem on SP end. | 1/14/02 |
| 100305 | 12/26/01 | Block activation causes association to abort | 2 | 3.1.0.2 | Closed |  | Test case rerun with SP to verify fixed by 3.1.0.2. | 1/14/02 |
| 100405 | 12/27/01 | Association aborts on range notification | 2 | 3.1.0.2 | Closed |  | Test reran verified is fixed by 3.1.0.2. | 1/14/02 |
| 100406 | 12/27/01 | Association aborts on SOA range notification = TRUE not on FALSE | 2 | 3.1.0.2 | Closed |  | Test reran verified is fixed by 3.1.0.2. | 1/14/02 |
| 101214 | 1/15/02 | EDR SP received 1000 SV disconnect notifications when 1 Block disconnect notification was expected | 2 |  | Closed | EDR SP did not submit block resync request on initial recovery; attempted to recover block information but specified not correct time; resync request supplied 1000 SV notifications instead of Block notification. | Test case passed. | 1/16/02 |
| 100696 | 1/04/02 | Old SP Create timers not running properly | 3 |  | Closed |  | Awaiting response from SP on test bed specific timer operation. | 1/16/02 |
| 100697 | 1/04/02 | NPAC processing failure on create range of SVs | 3 |  | Closed |  | NeuStar log files lost. Cannot reproduce the failure. | 1/16/02 |

Defect Fixed in Release 3.1.0.2

Incident 100641 SOA Range Notification Recovery after Audit create causes abort.

Discovered in Test Case 8.1.1.4.1.1

Not all attributes in the Range Notification were populated. In Release 3.1.0.2

the attributes in the notification message were populated correctly. Objects and attributes detailed below.

# Regression Test Cases

3.0 Regression Test Cases

8.1.1.4.1.1

9.2

NANC 48-5

2.0 Regression Test Cases

Audit_1

Audit_2

Audit_3

Audit_5

# Related Test Cases

## NANC 179

2.37

2.38

2.39

2.40

VersionRangeObjectCreation SEQ

range-object-creation SEQ

tn-version-id CHOICE

list-data SET OF no space

object-info SET OF no space

The fields list-data and object-info are the fields that 3.1.0.2 populated.