| Item Number Priority (H,M,L) | Description | Status/Resolution | Due Date |
| --- | --- | --- | --- |
| 1 H Test Plan | Development of test plan for turn-up and wireless to wireless inter-carrier testing. | Test plan is being developed by testing subgroup. A draft test plan template has been completed. Conference calls are scheduled 2/3/00 and 2/21/00, with a meeting on 2/29/00-3/1/00 to complete the test scripts. Jim Grasser has resigned as co chair and nominations for his replacement are requested. | 2Q00 |
| 2 H Inter-carrier Communications | Develop an inter-carrier communications process to enable quick and efficient wireless to wireless porting to accommodate our customer’s needs. | Inter-carrier communications process alternatives are being analyzed by the subgroup. Agreed guidelines are needed and referred evaluation to a CTIA Technical Team, open to all industry participants. CTIA NAG approved the report for distribution. A CTIA sponsored industry Forum to review the report is scheduled for 2/24-2/25/00 in Kansas City. | 1Q00 |
| 3 H Standards | Monitor standards development for MIN/MDN separation, and CLASS, LIDB, and SMS services in order to ensure timely manufacture of hardware and software for WNP. Monitor standards development for other enhanced services to ensure timely manufacture of hardware and software for WNP. | On 10/11/99, T1S1.6 , TR45.2 and T1P1.5 presented the standards overview. Standards for CCPN are complete. Continue gap analysis of network, billing and back office requirements A liaison will be sent to T1S1.6, TR45.2 and T1P1.5 requesting that JIP be made a wireless requirement to support billing | 4/30/00 |
| 4 H Network/OSS Infrastructure development monitoring. | Ensure timely availability of network and OSS hardware and software for WNP including switch upgrades, provisioning systems, and third party platforms. | All service providers should analysis their network, signaling, billing, and back office configurations to identify hardware and software upgrades required to support LNP. | 4/30/00 |
| 5 H MIN/MDN Separation | All MIN based wireless service providers must separate the MIN and MDN in all OSS and network elements in order to support nation wide roaming in a WNP environment. | MIN based providers must determine their functional specifications for separation of the MDN and MIN/MSID in all network and back office systems. | 4/30/00 |

| Item Number Priority (H,M,L) | Description | Status/Resolution | Due Date |
| --- | --- | --- | --- |
| 6 L MIN Administration | Monitor provision of MBI Administration | CTIA is developing the RFP for the MBI Administrator. CTIA recommends combining with IMSI management. Update subsequent to next IMSI forum. Implement MBI Administration | 4Q99 3Q01 |
| 7 H Wireless Participation | Knowledge and education for all wireless carriers on WNP implementation requirements. | Issue Public Notice to Industry requesting wireless participation in the WNPSC. Agreed to provide draft of content for Public Notice to expedite issuance of a Public Notice. WNPSC requested USTA, CTIA, PCIA, and OPASTCO to distribution information letter to its membership at 4/99 NANC meeting. CLOSED. | 6/99 |
| 8 M Milestone/ Tracking Report | A project management report that tracks WNP implementation schedule. | Revise existing milestone report to reflect WNP timeline and associated tasks as required. | 11/99 |
| 9 M NIIF LNP Guidelines | Monitor NIIF LNP issues and guidelines and update as needed for wireless number portability. | Monitor |  |
| 10 H Wireless Number Portability Report | Document wireless industry agreements and guidelines for Wireless Number Portability implementation | At the December 1999 meeting, section assignments were made and should be submitted to Anne Cummins, editor, by February 21, 2000. | 6/30/00 |